## Sheet1
59 Ham Street
[8 empty] | Period Highlight 1 | [8 empty] | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | WEEK
ACTIVITY |  | START | DURATION | START | DURATION | COMPLETE | PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
Demolition |  | 1 | 2 | 0 | 0 | 0%
Site set-up |  | 3 | 1 | 0 | 0 | 0%
Excavate and instal soakaways |  | 4 | 1 | 0 | 0 | 0%
Receive bulk deliveries |  | 5 | 1 | 0 | 0 | 0%
Set out foundations |  | 6 | 1 | 0 | 0 | 0%
Excavate foundations and concrete |  | 6 | 2 | 0 | 0 | 0%
Prep oversite |  | 7 | 1 | 0 | 0 | 0%
Foundation brickwork |  | 8 | 2 | 0 | 0 | 0%
Foul Drainage |  | 8 | 2 | 0 | 0 | 0%
service ducts |  | 8 | 2 | 0 | 0 | 0%
Beam and block floors |  | 10 | 1 | 0 | 0 | 0%
level and backfill around oversites |  | 11 | 1 | 0 | 0 | 0%
Brickwork first lift |  | 12 | 3 | 0 | 0 | 0%
Scaffold lift |  | 15 | 1 | 0 | 0 | 0%
Brickwork second lift |  | 15 | 3 | 0 | 0 | 0%
Scaffold lift |  | 17 | 1 | 0 | 0 | 0%
Widespan floors |  | 18 | 1 | 0 | 0 | 0%
Brickwork 3rd Lift |  | 18 | 3 | 0 | 0 | 0%
Scaffold Lift |  | 21 | 1 | 0 | 0 | 0%
Brickwork 4th lift |  | 21 | 3 | 0 | 0 | 0%
Scaffold to plate |  | 23 | 1 | 0 | 0 | 0%
Pitch Roof |  | 23 | 4 | 0 | 0 | 0%
Party Wall Blockwork |  | 24 | 2 | 0 | 0 | 0%
Instal chimney, Dormers and velux |  | 26 | 2 | 0 | 0 | 0%
Felt and batten |  | 27 | 3 | 0 | 0 | 0%
Roof coverings |  | 28 | 5 | 0 | 0 | 0%
Rainwater goods |  | 31 | 2 | 0 | 0 | 0%
PV Panels |  | 33 | 1 | 0 | 0 | 0%
Windows and Doors |  | 34 | 3 | 0 | 0 | 0%
Render |  | 37 | 6 | 0 | 0 | 0%
First fix Plumber |  | 37 | 3 | 0 | 0 | 0%
First fix Electrician |  | 39 | 3 | 0 | 0 | 0%
First fix carpenter |  | 42 | 3 | 0 | 0 | 0%
underfloor heating GF and screed |  | 43 | 3 | 0 | 0 | 0%
underfloor heating and screed FF |  | 44 | 3 | 0 | 0 | 0%
Plasterboard and tack |  | 46 | 3 | 0 | 0 | 0%
Wet Plaster |  | 49 | 3 | 0 | 0 | 0%
Cornice |  | 51 | 3 | 0 | 0 | 0%
Second fix Carpenter |  | 52 | 3 | 0 | 0 | 0%
Second fix Electrician |  | 52 | 3 | 0 | 0 | 0%
Second Fix Plumber |  | 52 | 3 | 0 | 0 | 0%
wall and floor tiling |  | 53 | 4 | 0 | 0 | 0%
Painting and decorating |  | 54 | 6 | 0 | 0 | 0%
snagging and finals |  | 58 | 4 | 0 | 0 | 0%
External works and services |  | 44 | 16 | 0 | 0 | 0%
Emergency Contact No. | 07920 759186